Strategic Work Plan Tasks:  November 2024

| STRATEGIC PRIORITY A: Develop a succession plan for key staff positions and strategy to maintain adequate staffing levels. |  |  |  |  |
| --- | --- | --- | --- | --- |
| OBJECTIVE 1: Define optimal organizational structure and key positions. |  |  |  |  |
| Activities/Tasks | Results | Board Lead – Others | Time frame |
| Task 1. Assess organizational structure, explore alternative structures and roles for key positions. | Potential new organizational chart showing modified or new roles for key positions. | Barb, Heather, Amy, Shannon | Completed 8/24. Org chart has been updated. |
| Task 2. Review staffing levels and budget implications of proposed alternative organizational structure(s). Determine areas where additional staff are needed. | Identification where additional staff are needed and budget implications. | Barb Heather Amy Shannon Treasurer | Completed 8-9/24. Bd discussion with Rebecca Chow along with subsequent review of proposed 2025 budget. |
| Task 3. Review job descriptions and roles of current staff and determine if changes are needed. | Updated job descriptions and develop new job descriptions as needed. | Heather Amy | Approved Cottage Manager 9/24. HH Manager and Exec Dir approved 10/24. |
| OBJECTIVE 2: Increase staff satisfaction and retention. |  |  |  |  |
| Task 1. Survey/interview staff to determine overall satisfaction with employment and reasons people might leave the organization. Revisit task annually. | List of key concerns of staff affecting professional fulfillment and reasons staff might leave the organization. Procedure for annual review | June Kip Nancy | Pilot in Fall 2024 Nov 2024 Conduct annually in Spring beginning in 2025 |
| Task 2. Review pay and benefit levels for similar organizations in the region and determine if the Hamlet’s pay and job conditions are competitive. | Comparison of the Hamlet’s pay, benefits, and working conditions with similar organizations in the area. | June | Sept/Oct 2024 November 2024 |
| Task 3: Develop a plan to address reasons identified in Task 1 and change pay and benefits plan if needed and if possible | A proposal addressing wage and benefits and other issues as needed. | June | After Tasks 1 and 2 are complete. |
| Task 4: Determine if proposed changes are financially feasible and develop budget proposal. | Budget proposal. | June | After Tasks 1 and 2 are complete. |
| Task 5: Develop a plan to express appreciation to staff. | Program to recognize and award staff for their work. | Amy, Barb, Nancy | October 2024 November 2024 |
| OBJECTIVE 3: Identify additional nursing or medical services for Hamlet House. |  |  |  |
| Task 1: Identify volunteer or paid Nursing or other medical service necessary for guiding daily resident care operations. | Retention of Nurse Practitioner or other needed nursing or medical consultation and/or services. | Karen Amy | Completed 10/24. Kai Sanborn to be retained. |
| Task 2: Develop triage guidelines. | Written guidance for medical situations faced by Hamlet House residents. | Karen Amy | TBD |
| OBJECTIVE 4: Explore partnering with other agencies to jointly provide services. |  |  |  |
| Task 1: Identify candidate services that may be provided through a partnership. | List of needed services that could be provided through a partnership arrangement. | All Board Heather Amy | December 2024 |
| Task 2: Identify potential agencies that could participate in a partnership arrangement. | List of potential partner agencies. | All Board, Heather, Amy | December 2024 |
| Task 3: Identify services most needed and most viable potential partners. | Proposal to provide specific services in partnership with specific agencies. | All Board Heather, Amy | December 2024 |
| OBJECTIVE 5: Develop a succession plan for key positions. |  |  |  |
| Task 1: Determine initial steps to be taken if a key position becomes vacant (Acting role or temporary hire or other step). | A plan of action to address a key position becoming vacant on short notice. | Karen Amy Heather | Completed 9/24. To be updated once HH resident position is filled. |
| Task 2: Identify potential current staff positions and staff who could move into key position. | Review of current staff and positions with potential to assume a key position. | Karen Amy Heather | TBD |
| Task 3: Identify training needed to prepare movement of a current or new staff position to move into key positions | Training plan to position staff for new role. | Karen, Amy Heather | TBD |

| STRATEGIC PRIORITY B: Improve financial management and monitoring and fundraising capabilities. |  |  |  |  |
| --- | --- | --- | --- | --- |
| OBJECTIVE 1: Increase Board financial expertise |  |  |  |
| Task 1. Recruit a new Treasurer for the board. | In progress. | Barb, Heather, Shannon | Chris Wiscomb joined Bd Oct/24 |
| Task 2: Determine other means to acquire financial expertise and advice. |  | Treasurer Heather | November 2024 |
| OBJECTIVE 2: Analyze current revenue and investments |  |  |  |  |
| Task 1. Review current revenue streams, i.e. Medicaid bed |  | Treasurer, Peggy, Heather, Amy | Completed 10/24 w/presentation to LI Hospital District |
| Task 2. Identify potential increases or new ongoing revenues |  | Karen, Amy, Kip, Shannon, Peggy | September 2024 Nov 2024 |
| OBJECTIVE 3: Develop performance measures for tracking financial health of the organization |  | Chris, Heather | Wait until new Treasurer is seated. Schedule. |
| OBJECTIVE 4: Develop a long-term fundraising strategy and plan. |  | Kip Peggy | December 2024? |
| Task 1: Review expertise on Fundraising committee and determine needs. |  | Kip, Shannon (Gov committee) | Ongoing |
| Task 2: Identify and cultivate donors |  | Kip, Fundraising Committee, Peggy | January 2025 |
| Task 3: Develop an annual fundraising cycle with events and milestones |  | Kip, Peggy, Fundraising Committee | January 2025 |
| Task 4: Plan for future major campaigns and fundraising targets |  | Kip, Heather, Peggy, Fundraising Comm, Treasurer, | January 2025 |

| STRATEGIC PRIORITY C: Review and update policies for facility and grounds management and operations. |  |  |  |  |
| --- | --- | --- | --- | --- |
| OBJECTIVE 1: Develop asset management plan for major buildings, ground maintenance, and equipment replacements and upgrades.. |
| Task 1. Analyze age and condition of facilities | Comprehensive report on facilities and their condition. Analysis of the age of the buildings to determine useful life and an appraisal of the value of the buildings in their current use? | Heather Consultant | Bd review budget item in Nov 2024. Work to be initiated January 2025. |
| Task 2: Develop a work plan for major renovations. | Working paper. | Heather, Dave, Consultant? | Based on results of Task 1 |
| Task 3: Review and update cottage garden/yard policy | Updated policy to be included in resident handbook. | GGK Heather Barb | Spring 2025 Rescheduled to November 2024 |

| OBJECTIVE 2: Plan for climate change and organization resiliency. |  |  |  |
| --- | --- | --- | --- |
| Task 1: Identify potential impacts of climate change on The Hamlet and its residents. | Working paper. | GGK Nancy | TBD |
| Task 2: Identify steps to reduce impact and the organization’s ability to respond to extreme weather conditions (heat, cold, flooding, etc.) | Plan to increase organization’s ability to manage extreme weather occurrences. | GGK Barb Nancy | TBD |
| Task 3: Update emergency power and inclement weather policies. | Board discussion/action | Amy Shannon Heather | TBD |
| Task 4: Develop (or Review) an Emergency Response Plan for Entire Hamlet |  | Heather Amy Shannon | TBD |
| OBJECTIVE 3: Review policy concerning use of the Gathering Place, including its kitchen and exercise areas |  |  |  |
| Task 1: Review current utilization and policy | Working Paper | TBD | TBD |
| Task 2: Develop new guidelines and initiatives. | Bd discussion/action | TBD | TBD |

| STRATEGIC PRIORITY D: Review and update policies addressing selection process for new residents and expectations for existing residents. |  |  |  |  |
| --- | --- | --- | --- | --- |
| OBJECTIVE 1: Develop and document criteria for selecting new residents. |  |  |  |  |
| Task 1. Document current process and criteria for selecting new residents. | Written documentation of current process and criteria for selecting new residents, | Heather, Angie, Shannon, Nancy | Completed 8/24. |
| Task 2. Develop policy stating selection criteria for new residents. | Policy with documented criteria for selection of new residents. | Heather Shannon | September November 2024 . |
| OBJECTIVE 2: Review current cottage resident policies |  |  |  |  |
| Task 1. Conduct legal review of policy for residing in cottages. | Review the policy by a legal professional | Heather Legal consultant | November 2024 |
| Task 2. Update cottage lease document and resident handbook. | Review both documents and update as needed for consistency. | Heather | TBD |