## Strategic Plan II 2025
2025-12-05 | Preliminary Draft 2026 Strategic Plan.
Activities/Tasks | Results | Board Lead – Others | Time frame | COMPLETE
STRATEGIC PRIORITY A: Develop a succession plan for key staff positions and strategy to maintain adequate staffing levels.
OBJECTIVE 1: Increase staff satisfaction and retention.
Task 1: Develop annual evaluation process and metrics for managers. | Process completed annually to provide feedback on work and evaluate salary levels. | Barbara, Karen, Mary Ann, AnnMarie | January 2026 | No
Task 2. Review pay and benefit levels for similar organizations in the region and determine if the Hamlet’s pay and job conditions are competitive. | Comparison of the Hamlet’s pay, benefits, and working conditions with similar organizations in the area. | June | Cottage Manager position to be reviewed after hired. | No
STRATEGIC PRIORITY B: Improve financial management and monitoring and fundraising capabilities.
OBJECTIVE 1: Increase Board financial expertise
Task 1. Review Treasurer description/responsibilities. |  | Barb, Heather
Task 2. Recruit a new Treasurer for the board. | Ongoing discussions through Governance Committee. | Barb, Heather, Vice Chair | Ongoing. | No
OBJECTIVE 2: Develop performance measures for tracking financial health of the organization |  | Heather | Postponed until new Treasurer on board. | No
STRATEGIC PRIORITY C: Develop a long-term fundraising strategy and plan.
OBJECTIVE 1: Identify and retain proposals for a fundraising consultant.
Task 1. Create a job description for the fundraising consultant. |  | Heather, Kip, and Barb
Task 2. Identify community members who may have knowledge of how to attain a fundraising consultant. |  | Entire board
Task 3. Create a list of potential fundraising consultants. |  | Heather
Task 4. Obtain LOIs from potential fundraising consultants. |  | Heather
Task 5. Hire fundraising consultant. |  | Heather
OBJECTIVE 2: Identify and cultivate donors.
Task 1: Develop an annual fundraising cycle with events and milestones. |  | Heather
Task 2. Develop a detailed fundraising plan with fundraising consultant. |  | Heather, Kip, fundraising consultant
OBJECTIVE 3: Determine capital and operating fundraising needs.
Task 1: Plan and execute new capital campaign to retire the Hamlet House mortgage.
Task 2: Create a plan/strategy to obtain funds for the financial assistance program.
STRATEGIC PRIORITY D: Improve emergency preparedness and response capabilities of the organization
OBJECTIVE 1: Refresh emergency plans for Hamlet House and LOHO.
Task 1: Consolidate and review the existing emergency plans. |  | June, Heather
OBJECTIVE 2: Identify utilities at risk during an extended emergency.
Task 1. Determine how to access potable water if power is out for an extended period of time. |  | Barb, June, Heather
Task 2. Evaluate backup power capacities (generator, solar, propane) |  | June, Heather
Task 3. Hire contractor to connect propane tank to generator. |  | Heather
OBJECTIVE 3: Further develop and implement a resident Emergency Preparedness communication plan.
Task 1. To enhance or further develop the existing emergency plan.
Task 2. To educate the community about the emergency plan.
Task 3. Schedule and execute Emergency Planning practice exercises.
STRATEGIC PRIORITY E: Nurture a sense of community among residents and between residents and the Board.
OBJECTIVE 1: Document and disseminate stories about Hamlet, its history and its importance with residents and the broader island community.
Task 1. Organize historical files. |  | Heather
Task 2. Create list of early members/founders to interview. |  | Barb, Bette?, Heather
Task 3. Interview and develop narrative. |  | Shari Lane, Ken Kortge, Wendy McClure, or Gretchen Wing, as volunteers? Plus Barb, Kip, and/or Heather.
Task 4. Develop timeline and list of venues to publish stories. |  | Gretchen?
OBJECTIVE 2: Survey cottage residents with prospective questions about what they would like to see in their community (e.g., more events, routine meetings with board)
Task 1. Determine the survey modality. |  | Board/staff
Task 2. Implement survey. |  | Polly, Mary Ann
Task 3. Present findings to the Board. |  | Polly, Mary Ann
Task 4. Present key findings to the residents.
Task 5. Integrate findings into future program planning.
OBJECTIVE 3: Create opportunities for board-resident conversations or communications. |  | Mary Ann, Heather, Volunteer Elizabeth S?
Task 1. Brainstorm type of activity.
Task 2. Poll board to determine the best date.
Task 3. Invite residents.
Task 4. Implement activity.

## Strategic Plan I
Activities/Tasks | Results | Board Lead – Others | Time frame | COMPLETE | JRC Comments
STRATEGIC PRIORITY A: Develop a succession plan for key staff positions and strategy to maintain adequate staffing levels.
OBJECTIVE 1: Define optimal organizational structure and key positions.
Task 1. Assess organizational structure, explore alternative structures and roles for key positions. | Potential new organizational chart showing modified or new roles for key positions. | Heather | Completed 8/24. Org chart has been updated. | Yes
Task 2. Review staffing levels and budget implications of proposed alternative organizational structure(s). Determine areas where additional staff are needed. | Identification where additional staff are needed and budget implications. | Barb, Heather, Amy, Shannon, Treasurer | Completed 8-9/24. Bd discussion with Rebecca Chow along with subsequent review of proposed 2025 budget. | Yes
Task 3. Review job descriptions and roles of current staff and determine if changes are needed. | Updated job descriptions and develop new job descriptions as needed. | Heather, Amy | Approved Cottage Manager 9/24. HH Manager and Exec Dir approved 10/24. | Yes
OBJECTIVE 2: Increase staff satisfaction and retention.
Task 1. Survey/interview staff to determine overall satisfaction with employment and reasons people might leave the organization. Revisit task annually. | List of key concerns of staff affecting professional fulfillment and reasons staff might leave the organization. Develop procedure for annual review | June, Kip, Heather | Completed 3/2025. Conduct annually beginning first quarter 2026. | Yes
Task 1.1 Survey approved with addition of ‘Anything else?’ added at the end to encourage additional information. Monitor results. | Distribute gift cards once survey is completed by each employee. | June, Kip | Completed May 2025 | Yes
Task 1.2 Develop an exit interview procedure. | Procedure/protocol to live in Board notebook and resident handbook. | June | Completed July 2025 | Yes
Task 1.3 Include staff survey procedure in Handbook revision. |  | Heather | Completed 4/2025. | Yes
Task 2. Review pay and benefit levels for similar organizations in the region and determine if the Hamlet’s pay and job conditions are competitive. | Comparison of the Hamlet’s pay, benefits, and working conditions with similar organizations in the area. | June | HH Mgr. complete May 2025. ED completed July 2025. Cottage Manager to be reviewed in Fall. | Track in SP ll
Task 3: Develop a plan to address reasons identified in Task 1 and change pay and benefits plan if needed and if possible | A proposal addressing wage and benefits and other issues as needed. | June | After Tasks 1 and 2 are complete. | Track in SP ll
Task 4: Determine if proposed changes are financially feasible and develop budget proposal. | Budget proposal. | June | After Tasks 1 and 2 are complete. | Track in SP ll
Task 5: Develop a plan to express appreciation to staff. Confirm budget line item. Brainstorm other ideas. | Program to recognize and award staff for their work. | Amy, June | Complete May 2025 | Yes
Task 6: Develop annual evaluation process and metrics for managers. | Process completed annually to provide feedback on work and evaluate salary levels. | Karen, Mary Ann, AnnMarie | Early Fall, 2025 | Track in SP ll
OBJECTIVE 3: Identify additional nursing or medical services for Hamlet House.
Task 1: Identify volunteer or paid Nursing or other medical service necessary for guiding daily resident care operations. | Retention of Nurse Practitioner or other needed nursing or medical consultation and/or services. | Karen, Amy | Completed 10/24. Kai Sanborn retained. | Yes
Task 2: Develop triage guidelines. | Written guidance for medical situations faced by Hamlet House residents. Cannot be done via WAC. | Karen, Amy | Completed June 2025. Karen and Kai will be available to staff as needed. | Yes
OBJECTIVE 4: Explore partnering with other agencies to jointly provide services.
Task 1: Identify candidate services that may be provided through a partnership. | List of needed services that could be provided through a partnership arrangement. | All Board, Heather, Amy | Completed 12/24. | Yes
Task 2: Identify potential agencies that could participate in a partnership arrangement. | List of potential partner agencies. | All Board, Heather, Amy | Completed 12/24. | Yes
Task 3: Identify services most needed and most viable potential partners. Review and edit handout. | Proposal to provide specific services in partnership with specific agencies. | Shannon | Completed 1/25. To be reviewed and updated quarterly (12/25). | Yes - periodic review required
OBJECTIVE 5: Develop a succession plan for key positions.
Task 1: Determine initial steps to be taken if a key position becomes vacant (Acting role or temporary hire or other step). | A plan of action to address a key position becoming vacant on short notice. | Karen, Amy, Heather | Completed 9/24. To be updated once HH resident position is filled. | Yes
Task 2: Identify potential current staff positions and staff who could move into key position. | Review of current staff and positions with potential to assume a key position. | Karen, Amy, Heather | Completed June 2025. Ani is now HH manager. | Yes
Task 3: Identify training needed to prepare movement of a current or new staff position to move into key positions | Training plan to position staff for new role using County and other training resources. | Karen, Amy, Heather | Ongoing, i.e. New Cottage Mgr w/ online Quick Books | Yes - periodic review required
STRATEGIC PRIORITY B: Improve financial management and monitoring and fundraising capabilities.
OBJECTIVE 1: Increase Board financial expertise
Task 1. Recruit a new Treasurer for the board. | Ongoing discussions through Governance Committee. | Barb, Heather, Shannon | Ongoing. Hire a Consultant? | Track in SP ll
Task 2: Determine other means to acquire financial expertise and advice. | John Bedeson joined finance committee. He has ideas for other committee members. | Chris, Heather | Completed 12/24. Reevaluate after new Treasurer on board. | Yes
OBJECTIVE 2: Analyze current revenue and investments
Task 1. Review current revenue streams, i.e. Medicaid bed |  | Treasurer, Peggy, Heather, Amy | Completed 10/24 w/presentation to LI Hospital District | Yes
Task 2. Identify potential increases or new ongoing revenues | Heather to check in regularly with Ann Grech re: grant station at library. | Heather | Quarterly. Next June 2025. | Yes - periodic review required
Task 3. Evaluate if cottages rent is representative of the industry. | Matt put summary of March results into file for future reference. | Heather, Cottage Mgr | Complete 3/25 | Yes
OBJECTIVE 3: Develop performance measures for tracking financial health of the organization |  | Heather | Postponed until new Treasurer on board. | Track in SP ll
OBJECTIVE 4: Develop a long-term fundraising strategy and plan.
Task 1: Review expertise on Fundraising committee and determine needs. | No new committee members as of yet, but some folks have offered to volunteer and assist in upcoming event. | Kip, Shannon (Gov Committee) Heather to assist |  | Track in SP ll
Task 2: Identify and cultivate donors |  | Kip, Fundraising Committee | To be completed once committee has additional members (Task 1) | Track in SP ll
Task 3: Develop an annual fundraising cycle with events and milestones | Speaker event scheduled for September 6, 2025. | Kip, Fundraising Committee | Now through 9/2025 | Track in SP ll
Task 4: Plan for future major campaigns and fundraising targets |  | Kip, Heather, Fundraising Comm, Treasurer, | Soiree in December 2025 | Track in SP ll
STRATEGIC PRIORITY C: Review and update policies for facility and grounds management and operations.
OBJECTIVE 1: Develop asset management plan for major buildings, ground maintenance, and equipment replacements and upgrades.
Task 1. Analyze age and condition of facilities | Comprehensive report on facilities and their condition. Inspection completed of each cottage. | Heather, Consultant | Completed Jan 2025. | Yes
Task 2: Develop a work plan for major renovations.
| Spreadsheet of maintenance items required as a result of January 2025 inspection | Heather, Dave, Cottage Mgr, Consultant | Shannon expand on Heather’s spreadsheet – 9/25 | Yes
Task 3: Review and update cottage garden/yard policy | Updated policy to be included in resident handbook. | Heather, Barb | Completed 2/2025. | Yes
OBJECTIVE 2: Plan for climate change and organization resiliency. This objective to be discussed by entire Board once a new Resident board member has been appointed.
Task 1: Identify potential impacts of climate change on The Hamlet and its residents. | Working paper. | ?? | TBD | No | remove/retire?
Task 2: Identify steps to reduce impact and the organization’s ability to respond to extreme weather conditions (heat, cold, flooding, etc.) | Plan to increase organization’s ability to manage extreme weather occurrences. | Barb | TBD | Track in SP ll
Task 3: Update emergency power and inclement weather policies. | Board discussion/action. | Shannon, June, Heather, Amy | Community event cancelled in July 2025 | Track in SP ll
Task 4: Develop (or Review) an Emergency Response Plan for Entire Hamlet |  | Heather, Amy, Shannon (to ask Brendan Cowdan/SJC to speak) |  | Track in SP ll
OBJECTIVE 3: Review policy concerning use of the Gathering Place, including its kitchen and exercise areas
Task 1: Review current utilization and policy | Working Paper | TBD | TBD | No | remove/retire?
Task 2: Develop new guidelines and initiatives. | Bd discussion/action | TBD | TBD | No | remove/retire?
STRATEGIC PRIORITY D: Review and update policies addressing selection process for new residents and expectations for existing residents.
OBJECTIVE 1: Develop and document criteria for selecting new residents.
Task 1. Document current process and criteria for selecting new residents. | Written documentation of current process and criteria for selecting new residents, | Heather, Angie, Shannon, Nancy | Completed 8/24. | Yes
Task 2. Develop policy stating selection criteria for new residents. | Policy with documented criteria for selection of new residents. | Heather, Shannon | Completed 10/24. | Yes
OBJECTIVE 2: Review current cottage resident policies
Task 1. Conduct legal review of policy for residing in cottages. | Review the policy by a legal professional | Heather, Legal Consultant | Completed 11/24. | Yes
Task 2. Update cottage lease document and resident handbook. | Review both documents and update as needed for consistency. | Heather, Cottage Mgr | Completed 5/25. | Yes
New Item to added to 2026 Strategic Plan – Fundraising Goal: Meals/Meds. Long Term Maintenance Plan was the goal in 2024. (however, funds are also required for existing programs).
1

## Idea Template
IDEA PLANNER
TOPIC |  | PLAN DUE |  |  | KEYWORDS | NAME
Technology |  | 2025-12-05 |  |  | Innovative, fresh, elegant | Team Dev
GOAL |  |  |  |  | OBJECTIVE
To win a grant or scholarships and a trip to Silicon Valley and Seattle. |  |  |  |  | Develop a technology solution for submission to the upcoming innovative app competition.
| TASKS |  | DUE DATE | Done? | STATUS | NOTES
-1 | Review competition rules |  | 2025-11-20 | No | -1 | Project resource links
-1 | Research prior winning technologies |  | 2025-11-23 | No | -1
0 | Develop & test app |  | 2025-11-25 | Pending | 0
-1 | Start BETA testing |  | 2025-11-30 | No | -1