## Strategic Plan II 2025
2026-01-14 | Preliminary Draft 2026 Strategic Plan.
Activities/Tasks | Results | Board Lead – Others | Time frame | COMPLETE
STRATEGIC PRIORITY A: Develop a succession plan for key staff positions and strategy to maintain adequate staffing levels.
OBJECTIVE 1: Increase staff satisfaction and retention.
Task 1: Develop annual evaluation process and metrics for managers. | Process completed annually to provide feedback on work and evaluate salary levels. | Barbara, Karen, Mary Ann, AnnMarie | February 2026 | No
Task 2. Review pay and benefit levels for similar organizations in the region and determine if the Hamlet’s pay and job conditions are competitive. | Comparison of the Hamlet’s pay, benefits, and working conditions with similar organizations in the area. | June | Cottage Manager position to be reviewed after hired. | No
STRATEGIC PRIORITY B: Improve financial management and monitoring and fundraising capabilities.
OBJECTIVE 1: Increase Board financial expertise
Task 1. Review Treasurer description/responsibilities. |  | Barb, Heather | Feb. 2026
Task 2. Recruit a new Treasurer for the board. | Ongoing discussions through Governance Committee. | Barb, Heather, Vice Chair | Ongoing. | No
OBJECTIVE 2: Develop performance measures for tracking financial health of the organization |  | Heather | Postponed until new Treasurer on board. | No
STRATEGIC PRIORITY C: Develop a long-term fundraising strategy and plan.
OBJECTIVE 1: Identify and retain proposals for a fundraising consultant.
Task 1. Create a job description for the fundraising consultant. |  | Heather, Kip, and Barb | March 2026
Task 2. Identify community members who may have knowledge of how to attain a fundraising consultant. |  | Entire board | Ongoing
Task 3. Create a list of potential fundraising consultants. |  | Heather
Task 4. Obtain LOIs from potential fundraising consultants. |  | Heather
Task 5. Hire fundraising consultant. |  | Heather
OBJECTIVE 2: Identify and cultivate donors.
Task 1: Develop an annual fundraising cycle with events and milestones. |  | Heather | Feb. 2026
Task 2. Develop a detailed fundraising plan with fundraising consultant. |  | Heather, Kip, fundraising consultant
OBJECTIVE 3: Determine capital and operating fundraising needs.
Task 1: Plan and execute new capital campaign to retire the Hamlet House mortgage. |  |  | April-June 2026
Task 2: Create a plan/strategy to obtain funds for the financial assistance program. |  |  | July-Sept. 2026
STRATEGIC PRIORITY D: Improve emergency preparedness and response capabilities of the organization
OBJECTIVE 1: Refresh emergency plans for Hamlet House and LOHO.
Task 1: Consolidate and review the existing emergency plans. |  | June, Heather | April 2026
OBJECTIVE 2: Identify utilities at risk during an extended emergency.
Task 1. Determine how to access potable water if power is out for an extended period of time. |  | Barb, June, Heather | Feb. 2026
Task 2. Evaluate backup power capacities (generator, solar, propane) |  | June, Heather | March 2026
Task 3. Hire contractor to connect propane tank to generator. |  | Heather | April 2026
OBJECTIVE 3: Further develop and implement a resident Emergency Preparedness communication plan.
Task 1. To enhance or further develop the existing emergency plan. |  |  | June 2026
Task 2. To educate the community about the emergency plan. |  |  | Sept. 2026
Task 3. Schedule and execute Emergency Planning practice exercises. |  |  | Oct. 2026
STRATEGIC PRIORITY E: Nurture a sense of community among residents, as well as between residents and the Board.
OBJECTIVE 1: Document and disseminate stories about Hamlet, its history and its importance with residents and the broader island community.
Task 1. Organize historical files. |  | Heather | Feb. 2026
Task 2. Create list of early members/founders to interview. |  | Barb, Bette?, Heather, Murray? | April-June 2026
Task 3. Interview and develop narrative. |  | Shari Lane, Ken Kortge, Wendy McClure, or Gretchen Wing, as volunteers? Plus Barb, Kip, and/or Heather. | April-June 2026
Task 4. Develop timeline and list of venues to publish stories. |  | Gretchen?
OBJECTIVE 2: Survey cottage residents with prospective questions about what they would like to see in their community (e.g., more events, routine meetings with board)
Task 1. Determine the survey modality. |  | Board/staff
Task 2. Implement survey. |  | Polly, Mary Ann
Task 3. Present findings to the Board. |  | Polly, Mary Ann
Task 4. Present key findings to the residents. |  | Polly, Mary Ann
Task 5. Integrate findings into future program planning.
OBJECTIVE 3: Create opportunities for board-resident conversations or communications. |  | Mary Ann, Heather, Volunteer Elizabeth S?
Task 1. Brainstorm type of activity.
Task 2. Poll board to determine the best date.
Task 3. Invite residents.
Task 4. Implement activity.

## Strategic Plan I
Activities/Tasks | Results | Board Lead – Others | Time frame | COMPLETE | JRC Comments
STRATEGIC PRIORITY A: Develop a succession plan for key staff positions and strategy to maintain adequate staffing levels.
OBJECTIVE 1: Define optimal organizational structure and key positions.
Task 1. Assess organizational structure, explore alternative structures and roles for key positions. | Potential new organizational chart showing modified or new roles for key positions. | Heather | Completed 8/24. Org chart has been updated. | Yes
Task 2. Review staffing levels and budget implications of proposed alternative organizational structure(s). Determine areas where additional staff are needed. | Identification where additional staff are needed and budget implications. | Barb, Heather, Amy, Shannon, Treasurer | Completed 8-9/24. Bd discussion with Rebecca Chow along with subsequent review of proposed 2025 budget. | Yes
Task 3. Review job descriptions and roles of current staff and determine if changes are needed. | Updated job descriptions and develop new job descriptions as needed. | Heather, Amy | Approved Cottage Manager 9/24. HH Manager and Exec Dir approved 10/24. | Yes
OBJECTIVE 2: Increase staff satisfaction and retention.
Task 1. Survey/interview staff to determine overall satisfaction with employment and reasons people might leave the organization. Revisit task annually. | List of key concerns of staff affecting professional fulfillment and reasons staff might leave the organization. Develop procedure for annual review | June, Kip, Heather | Completed 3/2025. Conduct annually beginning first quarter 2026. | Yes
Task 1.1 Survey approved with addition of ‘Anything else?’ added at the end to encourage additional information. Monitor results. | Distribute gift cards once survey is completed by each employee. | June, Kip | Completed May 2025 | Yes
Task 1.2 Develop an exit interview procedure. | Procedure/protocol to live in Board notebook and resident handbook. | June | Completed July 2025 | Yes
Task 1.3 Include staff survey procedure in Handbook revision. |  | Heather | Completed 4/2025. | Yes
Task 2. Review pay and benefit levels for similar organizations in the region and determine if the Hamlet’s pay and job conditions are competitive. | Comparison of the Hamlet’s pay, benefits, and working conditions with similar organizations in the area. | June | HH Mgr. complete May 2025. ED completed July 2025. Cottage Manager to be reviewed in Fall. | Track in SP ll
Task 3: Develop a plan to address reasons identified in Task 1 and change pay and benefits plan if needed and if possible | A proposal addressing wage and benefits and other issues as needed. | June | After Tasks 1 and 2 are complete. | Track in SP ll
Task 4: Determine if proposed changes are financially feasible and develop budget proposal. | Budget proposal. | June | After Tasks 1 and 2 are complete. | Track in SP ll
Task 5: Develop a plan to express appreciation to staff. Confirm budget line item. Brainstorm other ideas. | Program to recognize and award staff for their work. | Amy, June | Complete May 2025 | Yes
Task 6: Develop annual evaluation process and metrics for managers. | Process completed annually to provide feedback on work and evaluate salary levels. | Karen, Mary Ann, AnnMarie | Early Fall, 2025 | Track in SP ll
OBJECTIVE 3: Identify additional nursing or medical services for Hamlet House.
Task 1: Identify volunteer or paid Nursing or other medical service necessary for guiding daily resident care operations. | Retention of Nurse Practitioner or other needed nursing or medical consultation and/or services. | Karen, Amy | Completed 10/24. Kai Sanborn retained. | Yes
Task 2: Develop triage guidelines. | Written guidance for medical situations faced by Hamlet House residents. Cannot be done via WAC. | Karen, Amy | Completed June 2025. Karen and Kai will be available to staff as needed. | Yes
OBJECTIVE 4: Explore partnering with other agencies to jointly provide services.
Task 1: Identify candidate services that may be provided through a partnership. | List of needed services that could be provided through a partnership arrangement. | All Board, Heather, Amy | Completed 12/24. | Yes
Task 2: Identify potential agencies that could participate in a partnership arrangement. | List of potential partner agencies. | All Board, Heather, Amy | Completed 12/24. | Yes
Task 3: Identify services most needed and most viable potential partners. Review and edit handout. | Proposal to provide specific services in partnership with specific agencies. | Shannon | Completed 1/25. To be reviewed and updated quarterly (12/25). | Yes - periodic review required
OBJECTIVE 5: Develop a succession plan for key positions.
Task 1: Determine initial steps to be taken if a key position becomes vacant (Acting role or temporary hire or other step). | A plan of action to address a key position becoming vacant on short notice. | Karen, Amy, Heather | Completed 9/24. To be updated once HH resident position is filled. | Yes
Task 2: Identify potential current staff positions and staff who could move into key position. | Review of current staff and positions with potential to assume a key position. | Karen, Amy, Heather | Completed June 2025. Ani is now HH manager. | Yes
Task 3: Identify training needed to prepare movement of a current or new staff position to move into key positions | Training plan to position staff for new role using County and other training resources. | Karen, Amy, Heather | Ongoing, i.e. New Cottage Mgr w/ online Quick Books | Yes - periodic review required
STRATEGIC PRIORITY B: Improve financial management and monitoring and fundraising capabilities.
OBJECTIVE 1: Increase Board financial expertise
Task 1. Recruit a new Treasurer for the board. | Ongoing discussions through Governance Committee. | Barb, Heather, Shannon | Ongoing. Hire a Consultant? | Track in SP ll
Task 2: Determine other means to acquire financial expertise and advice. | John Bedeson joined finance committee. He has ideas for other committee members. | Chris, Heather | Completed 12/24. Reevaluate after new Treasurer on board. | Yes
OBJECTIVE 2: Analyze current revenue and investments
Task 1. Review current revenue streams, i.e. Medicaid bed |  | Treasurer, Peggy, Heather, Amy | Completed 10/24 w/presentation to LI Hospital District | Yes
Task 2. Identify potential increases or new ongoing revenues | Heather to check in regularly with Ann Grech re: grant station at library. | Heather | Quarterly. Next June 2025. | Yes - periodic review required
Task 3. Evaluate if cottages rent is representative of the industry. | Matt put summary of March results into file for future reference. | Heather, Cottage Mgr | Complete 3/25 | Yes
OBJECTIVE 3: Develop performance measures for tracking financial health of the organization |  | Heather | Postponed until new Treasurer on board. | Track in SP ll
OBJECTIVE 4: Develop a long-term fundraising strategy and plan.
Task 1: Review expertise on Fundraising committee and determine needs. | No new committee members as of yet, but some folks have offered to volunteer and assist in upcoming event. | Kip, Shannon (Gov Committee) Heather to assist |  | Track in SP ll
Task 2: Identify and cultivate donors |  | Kip, Fundraising Committee | To be completed once committee has additional members (Task 1) | Track in SP ll
Task 3: Develop an annual fundraising cycle with events and milestones | Speaker event scheduled for September 6, 2025. | Kip, Fundraising Committee | Now through 9/2025 | Track in SP ll
Task 4: Plan for future major campaigns and fundraising targets |  | Kip, Heather, Fundraising Comm, Treasurer, | Soiree in December 2025 | Track in SP ll
STRATEGIC PRIORITY C: Review and update policies for facility and grounds management and operations.
OBJECTIVE 1: Develop asset management plan for major buildings, ground maintenance, and equipment replacements and upgrades.
Task 1. Analyze age and condition of facilities | Comprehensive report on facilities and their condition. Inspection completed of each cottage. | Heather, Consultant | Completed Jan 2025. | Yes
Task 2: Develop a work plan for major renovations.
| Spreadsheet of maintenance items required as a result of January 2025 inspection | Heather, Dave, Cottage Mgr, Consultant | Shannon expand on Heather’s spreadsheet – 9/25 | Yes
Task 3: Review and update cottage garden/yard policy | Updated policy to be included in resident handbook. | Heather, Barb | Completed 2/2025. | Yes
OBJECTIVE 2: Plan for climate change and organization resiliency. This objective to be discussed by entire Board once a new Resident board member has been appointed.
Task 1: Identify potential impacts of climate change on The Hamlet and its residents. | Working paper. | ?? | TBD | No | remove/retire?
Task 2: Identify steps to reduce impact and the organization’s ability to respond to extreme weather conditions (heat, cold, flooding, etc.) | Plan to increase organization’s ability to manage extreme weather occurrences. | Barb | TBD | Track in SP ll
Task 3: Update emergency power and inclement weather policies. | Board discussion/action. | Shannon, June, Heather, Amy | Community event cancelled in July 2025 | Track in SP ll
Task 4: Develop (or Review) an Emergency Response Plan for Entire Hamlet |  | Heather, Amy, Shannon (to ask Brendan Cowdan/SJC to speak) |  | Track in SP ll
OBJECTIVE 3: Review policy concerning use of the Gathering Place, including its kitchen and exercise areas
Task 1: Review current utilization and policy | Working Paper | TBD | TBD | No | remove/retire?
Task 2: Develop new guidelines and initiatives. | Bd discussion/action | TBD | TBD | No | remove/retire?
STRATEGIC PRIORITY D: Review and update policies addressing selection process for new residents and expectations for existing residents.
OBJECTIVE 1: Develop and document criteria for selecting new residents.
Task 1. Document current process and criteria for selecting new residents. | Written documentation of current process and criteria for selecting new residents, | Heather, Angie, Shannon, Nancy | Completed 8/24. | Yes
Task 2. Develop policy stating selection criteria for new residents. | Policy with documented criteria for selection of new residents. | Heather, Shannon | Completed 10/24. | Yes
OBJECTIVE 2: Review current cottage resident policies
Task 1. Conduct legal review of policy for residing in cottages. | Review the policy by a legal professional | Heather, Legal Consultant | Completed 11/24. | Yes
Task 2. Update cottage lease document and resident handbook. | Review both documents and update as needed for consistency. | Heather, Cottage Mgr | Completed 5/25. | Yes
New Item to added to 2026 Strategic Plan – Fundraising Goal: Meals/Meds. Long Term Maintenance Plan was the goal in 2024. (however, funds are also required for existing programs).
1

## Idea Template
IDEA PLANNER
TOPIC |  | PLAN DUE |  |  | KEYWORDS | NAME
Technology |  | 2026-01-14 |  |  | Innovative, fresh, elegant | Team Dev
GOAL |  |  |  |  | OBJECTIVE
To win a grant or scholarships and a trip to Silicon Valley and Seattle. |  |  |  |  | Develop a technology solution for submission to the upcoming innovative app competition.
| TASKS |  | DUE DATE | Done? | STATUS | NOTES
-1 | Review competition rules |  | 2025-12-30 | No | -1 | Project resource links
-1 | Research prior winning technologies |  | 2026-01-02 | No | -1
0 | Develop & test app |  | 2026-01-04 | Pending | 0
-1 | Start BETA testing |  | 2026-01-09 | No | -1